## Sheet1
MIT ADT University, MIT School of Engineering
Department of Information Technology
B. Tech IT/DA
Project Scrum Board
Fake News Analysis and Detection (F.N.A.D)
Guide Name | Prof.Dr. Parnika Paranjape
Project Start Date | 14th September 2020
Project End Date
Project Id
Project Objectives | Fake News Analysis and Detection
Team Members | Enrollment Number |  |  | Name
| 2175050 |  |  | Rishab Jha
| 2175054 |  |  | Sahil Gavthankar
| 2175043 |  |  |  | Prashansa Bansal
| 21505 |  |  | Vivek Rote
Task Name | Sub Tasks | Task Status | Task Type | Priority | Assigned To | Assigned Date | Deadline | Estimated Hrs | Start Date | End Date | % Done | Estimated Hours | Actual Hours
[14 empty] | STATUS KEY | PRIORITY KEY | TASK TYPE
Research | Papers on related topics and deciding the right approach | Complete | Requirements Analysis | Medium | TM | 2020-09-14 |  |  | 2020-09-15 | 2020-09-17 | 100% |  |  | Not Started | High | Requirements Analysis
Dataset Selection | Finding the dataset which is suitable for our analysis | Complete | Requirements Analysis | Low | TM | 2020-09-17 |  |  | 2020-09-18 | 2020-09-21 | 100% |  |  | In Progress | Medium | Design
Environment Setup | Installing necessary packages and setting up ML environment on TM's devices | Complete | Requirements Analysis | Medium | TM | 2020-09-24 |  |  | 2020-09-26 | 2020-09-29 | 100% |  |  | Complete | Low | Modeling
GIthub | Inistialzing Github Repo and Branches | Complete | Requirements Analysis | High | TM | 2020-09-30 |  |  | 2020-09-30 | 2020-10-02 | 100% |  |  | On Hold |  | Coding and Implementation
Data Cleaning | MAJOR TASK :- Cleaning Data for required model MINOR TASK:- " Suitable techniques to clean data." | Complete | Coding and Implementation | High | SG VR | 2020-10-03 |  |  | 2020-10-04 | 2020-10-06 | 100% |  |  | Overdue |  | Validation and Testing
Data Manipulation | Manipulating Dataset to fit required Model and extracting suitable values | Complete | Coding and Implementation | High | VR PB | 2020-10-03 |  |  | 2020-10-06 | 2020-10-15 | 100% |  |  |  |  | Deployment
Data Visualization | Visualizing the final Dataset to see correlations and outliers | Complete | Coding and Implementation | High | VR PB | 2020-10-03 |  |  | 2020-10-16 | 2020-10-21 | 100%
EDA | Exploitory Data Analysis and understanding Dataset | Complete | Coding and Implementation | High | SG RJ | 2020-10-21 |  |  | 2020-10-22 | 2020-10-30 | 100% |  |  | 10%
Tokenization | A crucial process of converting NL into numbers | Complete | Coding and Implementation | High | RJ SG | 2020-11-01 |  |  | 2020-11-01 | 2020-11-04 | 100%
Training Data | Training Dataset with suitable parameters | Complete | Validation and Testing | Medium | PB SG | 2020-11-04 |  |  | 2020-11-04 | 2020-11-06 | 100% |  |  | 20%
Testing Data | Testing Dataset with suitable parameters | Complete | Validation and Testing | Medium | RJ VR | 2020-11-04 |  |  | 2020-11-04 | 2020-11-06 | 100% |  |  | 30%
Importing Alogorithms | Appropriate ML Algorithms | Complete | Deployment | Medium | PB VR | 2020-11-07 |  |  | 2020-11-08 | 2021-01-10 | 100% |  |  | 40%
Fiting Models | Fitting our model into Dataset | Complete | Coding and Implementation | High | TM | 2020-11-09 |  |  | 2020-11-09 | 2021-01-10 | 100% |  |  | 50%
Model testing | Testing our model on Train and Test Dataset | Complete | Modeling | High | TM | 2020-11-10 |  |  | 2020-11-10 | 2021-01-25 | 100% |  |  | 60%
Accuracy testing | Testing our accuracy of model | Complete | Validation and Testing | High | TM | 2020-11-10 |  |  | 2020-11-11 | 2021-02-02 | 100% |  |  | 70%
UI Implementation | Making a python based UI | Complete | Design | High | RJ SG | 2021-02-03 |  |  | 2021-02-05 | 2021-05-05 | 100% |  |  | 80%
90%
100%
Total Hours | 0
Project Progress